## Sheet1
"C"
COUNTY GOVERNMENT OF NYANDARUA
PROJECT IMPLEMENTATION STATUS AS AT 31ST December, 2025 ( FY 2025-26)
DATE: 10/10/2025
Sector | Project Name | Project Location | Budget Allocation ( Kshs.) | Implementation status (%) | Source of Funding (GoK/donor) | Remarks
FINANCE, ECONOMIC PLANNING, ICT & REVENUE
County fund- Development | Nyandarua County Trade Development and Investment Authority Fund |  | 25000000 | 0% | CGN | Not yet started
KDSP | Kenya Devolution Support Programme Phase I- B/f FY 2021-22 |  | 83211329 | 0% | World bank | transferred to CRF
Pending Bills | Provision for Development pending Bills |  | 152712964 | 20% | CGN | Processing ongoing
ICT & E-government Services | Installation of Surveillance Systems |  | 500000 | 0% | CGN | Not yet started
| Installation of Local Area Network (LAN) |  | 1000000 | 0% | CGN | Not yet started
| Establishment and equipping of ICT Hub (Matopeni, Ol Joro Orok and Kwa Njora) |  | 3000000 | 0% | CGN | Not yet started
| Extension of the National Optic Fibre. Backbone Infrastructure (NOFBI) to more County offices/WAN and free wifi hotspots |  | 4000000 | 0% | CGN | Not yet started
| intergrated county information system (including health facilities integration) |  | 3500000 | 0% | CGN | Not yet started
PUBLIC SERVICE, ADMINISTRATION AND DEVOLUTION
KDSP | Kenya Development Support Program Level 2 |  | 352500000 | 0% | World bank | Site visit and data collection ongoing
HEALTH SERVICES
Infrastructure and Equipment | Fencing of Olkalou disposal site | Olkalou Sub-County | 2000000 | 0% | CGN | New project
| Upgrade of Bamboo health center radiology completion and equipping - Kinangop subcounty | Kinangop Sub-County | 6500000 | 20% | CGN | Ongoing
| Upgrade of Ndaragwa health center radiology completion- ndaragwa subcounty | Ndaragwa Sub-County | 8700000 | 0% | CGN | Ongoing
| Upgrade of Ndaragwa health center Morgue | Ndaragwa Sub-County | 4000000 | 0% | CGN | New project
| Upgrade of Ngano Health Centre - Ol'Joro'Orok Subcounty | Ol'Joro'Orok Subcounty | 5000000 | 0% | CGN | New project
| Infrastructure upgrade (Construction of staff quarters) - Charagita dispensary | Charagita ward | 5000000 | 0% | CGN | New project
| Mirangine Health Centre- Solarization | Mirangine ward | 1500000 | 0% | CGN | New project
| Upgrade of Manunga health center- Kipipiri Subcounty | Kipipiri Sub-County | 3074615 | 20% | CGN | Ongoing
| Completion of Munyeki Dispensary-Karau ward | Karau Ward | 5500000 | 85% | CGN | Ongoing
| JM Mashujaa complex | Olkalou Sub-County | 100000000 | 60% | CGN | Construction taken over by the the National Government
| Upgrage of Shamata health center | Shamata ward | 5500000 | 70% | CGN | Ongoing
| Shamata health center -Morgue | Shamata ward | 2000000 | 0% | CGN | New phased project
| Renovation of Turasha dispensary in Githioro ward | Githioro ward | 2000000 | 0% | CGN | New project
| Equipping and operationalization of Mirangine CDC | Olkalou Sub-County | 20000000 | 0% | CGN | New project
| Departmental offices renovations & upgrade | Olkalou Sub-County | 1000000 | 0% | CGN | New project
| Baari Health Centre- Administration Block -Kiriita | Kiriita ward | 2500000 | 0% | CGN | New project
| Huhoini Dispensary maternity wing completion |  | 2000000 | 70% | CGN | Ongoing-finishes works
| Mumui dispensary fencing |  | 500000 | 0% | CGN | New project
| Construction of Passenga dispensary Rurii-Fencing and toilet completion | Rurii ward | 1900000 | 85% | CGN | Ongoing
| Construction of Kagaa dispensary toilet - Karau ward | Karau Ward | 600000 | 0% | CGN | New project
| Improvement of Njabini health center | Njabini Kiburu ward | 3000000 | 0% | CGN | New project
EDUCATION, TECHNICAL TRAINING, CULTURE, GENDER & SOCIAL PROTECTION
Early Childhood Development Education (ECDE) | Equipping of ECDE Across the County @ 1M per Ward | Countywide | 25000000 | 0 | CGN | Not yet started
| Equipping of ECDE's with Child friendly kits - Mirangine Ward | Mirangine Ward | 600000 | 0 | CGN | Not yet started
| Digitization of ECDE Learning (Phase II), Countywide | Countywide | 3000000 | 0 | CGN | Not yet started
| Construction of ECDE Classroom | Githabai Ward | 1800000 | 0 | CGN | Not yet started
| Construction of ECDE toilet | Githabai Ward | 800000 | 0 | CGN | Not yet started
| Construction and equipping phase II ECDE centre with child friendly equipment (including landscapping and beautification) | Githabai Ward | 7900000 | 0 | CGN | Not yet started
| Construction of 3 door toilet (bio-digester system) with a urinal phase II ECDE centre | Githabai Ward | 1500000 | 0 | CGN | Not yet started
| Construction of Kiamweri ECDE Class and toilet | Njabini Ward | 1100000 | 0 | CGN | Not yet started
| Construction of Mutongwe ECDE Classroom | Njabini Ward | 1800000 | 0 | CGN | Not yet started
| Construction of Makutano ECDE Toilet | Engineer Ward | 800000 | 0 | CGN | Not yet started
| Construction of Kiria ECDE Toilet | North Kinangop Ward | 800000 | 0 | CGN | Not yet started
| Renovation of Kimuri ECDE | Murungaru Ward | 500000 | 0 | CGN | Not yet started
| Construction of St. Peters ECDE Classroom | Githioro Ward | 2000000 | 0 | CGN | Not yet started
| Construction of Rurii B ECDE Toilet | Githioro Ward | 800000 | 0 | CGN | Not yet started
| Construction of 2No.Toilets - Miti-itano and Githunguri ECDEs | Wanjohi Ward | 1600000 | 0 | CGN | Not yet started
| Construction of Huhirio B classroom and toilet | Wanjohi Ward | 2600000 | 0 | CGN | Not yet started
| Renovation of Mubau & Michoe ECDE Classrooms | Wanjohi Ward | 1500000 | 0 | CGN | Not yet started
| Construction of Simba ECDE Toilet | Kaimbaga Ward | 700000 | 0 | CGN | Not yet started
| Construction of Kanyiriri ECDE Toilet | Karau Ward | 600000 | 0 | CGN | Not yet started
| Construction of St. Thomas ECDE Toilet and Kitchen | Rurii Ward | 2000000 | 0 | CGN | Not yet started
| Construction of Malan ECDE Classroom | Rurii Ward | 1800000 | 0 | CGN | Not yet started
| Construction of Silanga ECDE Toilet | Rurii Ward | 800000 | 0 | CGN | Not yet started
| Construction of Kanjuiri ECDE Toilet - | Kanjuiri Ward | 800000 | 0 | CGN | Not yet started
| Construction of Chiira ECDE Toilet | Kanjuiri Ward | 800000 | 0 | CGN | Not yet started
| Construction of Ndothua ECDE Toilet | Kanjuiri Ward | 800000 | 0 | CGN | Not yet started
| Construction of Kang'athia ECDE Toilet | Kanjuiri Ward | 800000 | 0 | CGN | Not yet started
| Construction of ECDE Classroom- Miiri | Mirangine Ward | 1600000 | 0 | CGN | Not yet started
| Construction of ECDE Toilet- Kanyotu | Mirangine Ward | 700000 | 0 | CGN | Not yet started
| Construction of Sabugo pry ECDE toilet | Charagita Ward | 800000 | 0 | CGN | Not yet started
| Construction of Muchemi pry ECDE toilet | Charagita Ward | 800000 | 0 | CGN | Not yet started
| Construction of ECDE Classroom | Gathanji Ward | 1800000 | 0 | CGN | Not yet started
| Construction of Mutanga ECDE Classroom | Gathanji Ward | 1800000 | 0 | CGN | Not yet started
| Construction of ECDE Toilet | Gathanji Ward | 800000 | 0 | CGN | Not yet started
| Construction of 2 No. ECDE Classrooms | KIiriita Ward | 3600000 | 0 | CGN | Not yet started
| Construction of ECDE Toilet(s) | Kiriita Ward | 800000 | 0 | CGN | Not yet started
| Construction and equipping Njamba ECDE Centre | Shamata Ward | 4000000 | 0 | CGN | Not yet started
| Construction of 2 No. ECDE Toilets (Riverside and Gikingi | Gatimu Ward | 1800000 | 0 | CGN | Not yet started
| Construction of Kanyagia ECDE classroom | Ndaragwa central Ward | 1500000 | 0 | CGN | Not yet started
| Construction of Nyonjoro ECDE classroom | Ndaragwa central Ward | 1500000 | 0 | CGN | Not yet started
| Construction of Ndururi ECDE classroom | Ndaragwa central Ward | 1500000 | 0 | CGN | Not yet started
| Tank Stand, guttering and fiitings for ECDEs FY 2024-25- | Leshau Pondo Ward | 870000 | 0 | CGN | Not yet started
| Renovation of Simbara ECDE, Njamba ECDE Class and Gakoe ECDE toilet- | Shamata Ward | 2398753 | 100 | CGN | Not yet paid
Vocational Education and Training Development | Vocational Training Centre for Jua Kali Artisan Specialized Training and equipment- | Kaimbaga Ward | 1400000 | 0 | CGN | Not yet started
| Equipping of Shauri VTC with modern tools and equipment - | Leshau Pondo Ward | 1500000 | 0 | CGN | Not yet started
| Equipping of Geta Polytechnic | Geta Ward | 4000000 | 0 | CGN | Not yet started
| Equipping workshop at Wanjohi VTC - | Wanjohi Ward | 400000 | 0 | CGN | Not yet started
| Construction of sanitation facilities at Wanjohi VTC - | Wanjohi Ward | 2000000 |  | CGN | Not yet started
| Construction of twin workshop at Wanjohi VTC | Wanjohi Ward | 5000000 |  | CGN | Not yet started
| Construction of Njabini VTC sanitation facilities - | Njabini Ward | 1200000 |  | CGN | Not yet started
| Fencing Nandarasi VTC - | North Kinangop Ward | 2000000 |  | CGN | Not yet started
| Upgrade of T-Rose VTC - | Charagita Ward | 1000000 |  | CGN | Not yet started
| Construction of Shamata VTC sanitation facilities - Shamata Ward | Shamata Ward | 1200000 |  | CGN | Not yet started
| Upgrade of Ol' Bolosat polytechnic - | Shamata Ward | 2000000 |  | CGN | Not yet started
| Construction of Nandarasi VTC administration block (Phase II) - | North Kinangop Ward | 3500000 |  | CGN | Not yet started
| Support to Nyandarua University College | Countywide | 15000000 |  | CGN | Not yet started
Cultural Heritage | Supply and deliver traditional performance attire (Uniforms)- Rurii Ward | Rurii Ward | 400000 | 0 | CGN | Not yet started
| Supply and deliver uniforms and cultural regalia for identified cultural groups | Countywide | 2145000 | 0 | CGN | Not yet started
| Supply and deliver cultural festival and exhibition materials- Including branding and marketing materials | Countywide | 2000000 |  | CGN | Not yet started
| Completion of Gordon Cultural and mentorship centre (Phase 2) - Engineer | Engineer Ward | 13924940 | 80% | CGN | Ongoing
| Toilet for Kiharo Community- Weru Ward | Weru Ward | 700000 |  | CGN | Not yet started
| Construction of Gatondo social hall (Phase I) - Wanjohi Ward | Wanjohi Ward | 3000000 |  | CGN | Not yet started
Library Services | Construction of modern Ol'Kalou Community Library | karau Ward | 17953775.15 | 0 | CGN | Ongoing
Gender and Social Protection | Supply of duvets/warmers to the needy elderly- Githabai | Githabai Ward | 2500000 | 0 | CGN | Not yet started
| Gender empowerment program- Githabai | Githabai Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver 16No. 100 seater capacity tents- Githabai | Githabai Ward | 2000000 | 0 | CGN | Not yet started
| Provision and distribution of hygiene kits to vulnerable boys and girls | Countywide | 3500000 | 0 | CGN | Not yet started
| Supply and distribution of Social assistance (foodstaff and other basic items) to the vulnerable groups- (child - headed families, the elderly, PWDs, the chronically sick, poverty stricken) - | County wide | 4500000 | 0 | CGN | Not yet started
| Economic empowerment (Facilitation of income generating activities) of vulnerable groups countywide- Persons with HIV, Orphans and other vulnerable children, GBV victims, teen mothers, severely poverty-stricken | Countywide | 4500000 | 0 | CGN | Not yet started
| Supply and deliver diapers to needy learners in special schools | Countywide | 800000 | 0 | CGN | Not yet started
| Economic empowerment of PWDS | Countywide | 1500000
| Supply and deliver assistive devices to various categories of PWDs (the blind, the deaf, those with albinism, those with mobility impairment, the bedridden etc) | Countywide | 2000000 | 0 | CGN | Not yet started
| Procurement of complete public address system with generators and projectors | Countywide | 3000000 | 0 | CGN | Not yet started
| Procurement of public address system with generators - Nyandarua Cancer Support Group | Countywide | 1000000 | 0 | CGN | Not yet started
| Procurement of Education Dept. Tent and Chairs | County HQs | 500000 | 0 | CGN | Not yet started
| Supply and deliver water tanks | Magumu Ward | 3500000 | 0 | CGN | Not yet started
| Supply and deliver tents and chairs for social welfare groups - Magumu Ward | Magumu Ward | 2700000 | 0 | CGN | Not yet started
| Support to organised groups to acquire driving licences - Magumu Ward | Magumu Ward | 4000000 | 0 | CGN | Not yet started
| Social support to women groups and catering groups (Kitchen ware etc)- Nyakio Ward | Nyakio Ward | 1000000 | 0 | CGN | Not yet started
| Specialized training to youth and boda boda groups- Nyakio | Nyakio Ward | 1500000
| Support to social groups with Public address systems - Nyakio | Nyakio Ward | 1000000 | 0 | CGN | Not yet started
| Support to bodaboda groups with assorted equipment- Nyakio | Nyakio Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups - Nyakio Ward | Nyakio Ward | 1500000 | 0 | CGN | Not yet started
| Support to organised social groups to acquire driving licences- Githabai Ward | Githabai Ward | 2000000 | 0 | CGN | Not yet started
| Purchase of specialized equipment (Complete set of 2No. public address system) - | Githabai Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups - Njabini Ward | Njabini Ward | 1300000 | 0 | CGN | Not yet started
| Supply and deliver 500l plastic tanks to the needy families - Njabini Ward | Njabini Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver blankets to the needy elderly- Njabini Ward | Njabini Ward | 500000 | 0 | CGN | Not yet started
| Social support to Women groups (Kitchen ware etc)- Njabini Ward | Njabini Ward | 600000 | 0 | CGN | Not yet started
| Social assistance to the vulnerable with foodstuff- Njabini | Njabini Ward | 1000000 | 0 | CGN | Not yet started
| Specilaised training to organised social groups (bodaboda operators etc)- Njabini | Njabini Ward | 1000000
| Support to bodaboda groups with Motorbikes - Gathaara Ward | Gathaara Ward | 1250000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups - Gathaara Ward | Gathaara Ward | 3000000 | 0 | CGN | Not yet started
| Supply of assorted public address systems for Fanta Community welfare group - Gathaara Ward | Gathaara Ward | 600000 | 0 | CGN | Not yet started
| Supply of 500l plastic tanks- Chobe, Giiko and Utheri wa Chobe- Engineer | Engineer Ward | 4200000 | 0 | CGN | Not yet started
| Women empowerment on public food safety through clean energy- Engineer | Engineer Ward | 4500000 | 0 | CGN | Not yet started
| Supply and delivery of public address systems - Kanyugi & Wendani Welfare groups- Engineer Ward | Engineer Ward | 700000 | 0 | CGN | Not yet started
| Supply and deliver Tents to social welfare groups - Githioro Ward | Githioro Ward | 2000000 | 0 | CGN | Not yet started
| Purchase of specialized equipment (Complete set of 2No. public address system) - Githioro Ward | Githioro Ward | 1000000 | 0 | CGN | Not yet started
| Supply and delivery of tents (100 seat capacity) to social welfare groups - Wanjohi Ward | Wanjohi Ward | 2000000 | 0 | CGN | Not yet started
| Supply and delivery of public address systems to youth groups - Wanjohi Ward | Wanjohi Ward | 3000000 | 0 | CGN | Not yet started
| Support to Church groups with Tents and chairs and complete set public address system - Wanjohi Ward | Wanjohi Ward | 2000000 | 0 | CGN | Not yet started
| Supply and deliver 500Litres plastic tanks to the needy - Kipipiri Ward | Kipipiri Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver Tents to social welfare groups - Kaimbaga Ward | Kaimbaga Ward | 1500000 | 0 | CGN | Not yet started
| Supply and deliver school uniforms and aprons - Kaimbaga Ward | Kaimbaga Ward | 2500000 | 0 | CGN | Not yet started
| Issuance of driving licences - Kaimbaga Ward | Kaimbaga Ward | 1000000
| Supply and deliver pool tables, spades & mattocks, power saws and sufurias to social welfare groups - Kaimbaga Ward | Kaimbaga Ward | 650000 | 0 | CGN | Not yet started
| Supply and deliver a public address system- Kaimbaga Ward | Kaimbaga Ward | 500000 | 0 | CGN | Not yet started
| Supply and deliver a small container for Kiganjo A SHG -Kaimbaga Ward | Kaimbaga Ward | 400000 | 0 | CGN | Not yet started
| Supply and deliver block making machine, Branding machine, poshomill, chuff cutter and salon equipments - Kaimbaga Ward | Kaimbaga Ward | 1200000 | 0 | CGN | Not yet started
| Procurement and distribution of water tanks to needy households - Lower- Kaimbaga Ward | Kaimbaga Ward(Lower) | 4000000 | 0 | CGN | Not yet started
| Procurement and distribution of water tanks to needy households - Upper - Kaimbaga Ward | Kaimbaga Ward(Upper) | 5000000 | 0 | CGN | Not yet started
| Social support to social groups with tents and plastic chairs - Karau Ward | Karau Ward | 2500000 | 0 | CGN | Not yet started
| Support to bodaboda groups - Karau Ward | karau Ward | 1000000 | 0 | CGN | Not yet started
| Social support to social groups with public address systems - Karau Ward | Karau Ward | 1000000 | 0 | CGN | Not yet started
| Social support to Ol'Kalou Lorry tranport services - Karau Ward | Karau Ward | 200000 | 0 | CGN | Not yet started
| Social support to women welfare groups - Rurii Ward | Rurii Ward | 600000 | 0 | CGN | Not yet started
| Support to bodaboda groups (Tyres, umbrellas, training)- Rurii Ward | Rurii Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver plastic tanks to the needy families - Rurii Ward (upper) | Rurii Ward (upper) | 1200000 | 0 | CGN | Not yet started
| Supply and deliver plastic tanks to the needy families - Rurii Ward (lower) | Rurii Ward (lower) | 2000000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups- Rurii Ward | Rurii Ward | 1800000 | 0 | CGN | Not yet started
| Supply and deliver tents and chairs to social welfare groups (Kamuyu, Kanyotu, Kihuho/Kirathimo, Makara & Gathiriga A)- Mirangine Ward | Mirangine Ward | 1750000 | 0 | CGN | Not yet started
| Social support to Men, women and youth social groups- Mirangine Ward | Mirangine Ward | 2000000 | 0 | CGN | Not yet started
| Supply and deliver assorted motor cycle tyres - Kaimbaga Ward | Kaimbaga Ward | 1500000 | 0 | CGN | Not yet started
| Social support to women groups - Kaimbaga Ward | Kaimbaga Ward | 2700000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups - Kanjuiri Ward | Kanjuiri Ward | 3000000 | 0 | CGN | Not yet started
| Supply and deliver plastic chairs for social welfare groups tents- Kanjuiri Ward | Kanjuiri Ward | 2000000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups- Charagita Ward | Charagita Ward | 2000000 | 0 | CGN | Not yet started
| Social support to women groups (utensils) - Charagita Ward | Charagita Ward | 1000000 | 0 | CGN | Not yet started
| Social support to social welfare groups - Weru Ward | Weru Ward | 3000000 | 0 | CGN | Not yet started
| Support to bodaboda groups - Gatimu Ward | Gatimu Ward | 1000000 | 0 | CGN | Not yet started
| Social economic support to men, women and youth groups- Gatimu Ward | Gatimu Ward | 3000000 | 0 | CGN | Not yet started
| Supply of tents to welfare groups - Gikima- Gathanji | Gathanji Ward | 1000000 | 0 | CGN | Not yet started
| Support to social groups (Specialized Training) Gathanji Ward | Gathanji Ward | 1000000 | 0 | CGN | Not yet started
| Social support to women welfare groups (Kitchen ware, protective clothing etc)- Kiriita Ward | Kiriita Ward | 800000
| Social support to social groups (Tents, Chairs, and other equipment)- Kiriita Ward | Kiriita Ward | 2500000 | 0 | CGN | Not yet started
| Supply and deliver tents to social welfare groups - Leshau Pondo Ward | Leshau Pondo Ward | 750000 | 0 | CGN | Not yet started
| Supply and deliver Motor bikes to bodaboda groups - Leshau Pondo Ward | Leshau Pondo Ward | 900000 | 0 | CGN | Not yet started
| Social support to Barber shops/salons with specialized tools and accessories - Leshau Pondo Ward | Leshau Pondo Ward | 400000 | 0 | CGN | Not yet started
| Social support to youth groups (printer, desktop, laptop and label printer) - Leshau Pondo Ward | Leshau Pondo Ward | 1500000 | 0 | CGN | Not yet started
| Social support to catering groups (Kitchen ware etc)- Leshau Pondo Ward | Leshau Pondo Ward | 400000 | 0 | CGN | Not yet started
| Purchase of specialized equipment (Complete set of 2No. public address system) - Leshau Pondo Ward | Leshau Pondo Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver and install 2No. 10000L Plastic tanks - Leshau Pondo Ward | Leshau Pondo Ward | 300000 | 0 | CGN | Not yet started
| Supply and deliver plastic chairs for social welfare groups - Leshau Pondo Ward | Leshau Pondo Ward | 500000 | 0 | CGN | Not yet started
| Social assistance to the vulnerable with foodstuff (Christmas)- Leshau Pondo Ward | Leshau Pondo Ward | 1000000 | 0 | CGN | Not yet started
| Social support to women and youth groups - Ndaragwa Central Ward | Ndaragwa central Ward | 2000000 | 0 | CGN | Not yet started
| Social support to welfare groups with catering equipment - Ndaragwa Central Ward | Ndaragwa central Ward | 1000000 | 0 | CGN | Not yet started
| Supply and deliver plastic chairs to social welfare groups - Ndaragwa Central Ward | Ndaragwa central Ward | 1000000 | 0 | CGN | Not yet started
| Support to bodaboda groups with umbrellas, helmets, tyres- Ndaragwa Central Ward | Ndaragwa central Ward | 2500000 | 0 | CGN | Not yet started
| Supply and deliver plastic tanks to the needy families - Ndaragwa Central Ward | Ndaragwa central Ward | 4000000 | 0 | CGN | Not yet started
| Support to bodaboda groups with tyres - Murungaru Ward | Murungaru Ward | 1000000 | 0 | CGN | Not yet started
| Social support to welfare groups with catering equipment - Murungaru Ward | Murungaru Ward | 1000000 | 0 | CGN | Not yet started
| Supply and delivery of tents- Murungaru Ward | Murungaru Ward | 1000000 | 0 | CGN | Not yet started
| Social support to social groups- Shamata Ward | Shamata Ward | 4000000 | 0 | CGN | Not yet started
| Supply and delivery of tents( 100 chairs capacity ) and chairs for Kiganjo A and Fredha self help groups. |  | 500000 | 0 | CGN | Not yet started
| Supply and delivery of tents( 100 chairs capacity ) and chairs for kona self help group. | Geta Ward | 295000 | 0 | CGN | Not yet started
| Supply and delivery of specialized public address system- FY 2024-25 M/S PUWAN INVESTMENT |  | 999560 | 100 | CGN | Not yet paid
WATER, SANITATION, ENVIRONMENT,TOURISM, NATURAL RESOURCES AND CLIMATE CHANGE
Water Resource Management | MAGUMU WARD
| Assorted pipes and Accessories- Magumu Ward | Magumu | 2800000 | 0% | CGN | Site visit and data collection ongoing
GITHABAI WARD
| Repair works- Kaugi borehole- Submersible pump, hybrid inverter, KPLC connection and commissioning | Githabai | 1600000 | 0% | CGN | Site visit and data collection ongoing
| Miti-iri borehole, Nyakio borehole, Heni borehole- plumbing works and plumbings accessories | Githabai | 1000000 | 0% | CGN | Site visit and data collection ongoing
| NYAKIO WARD |  |  | 0% | CGN | Site visit and data collection ongoing
| Supply of assorted pipes and accessories | Nyakio | 2000000 | 0% | CGN | Site visit and data collection ongoing
NJABINI WARD
| Churiri borehole-Equipping with solar powered submersible pump and installation of solars | Njabini | 4000000 | 0% | CGN | Site visit and data collection ongoing
| Churiri borehole-Construction of water tower and erection of 2No. 10M3 plastic tanks | Njabini | 1700000 | 0% | CGN | Site visit and data collection ongoing
| Replacement of pump motor - Coloboise Borehole WP | Njabini | 500000 | 0% | CGN | Site visit and data collection ongoing
| GATHAARA |  |  | 0% | CGN | Site visit and data collection ongoing
| Supply and laying of assorted pipes and fittings - Gathaara Ward | Gathaara | 1000000 | 0% | CGN | Site visit and data collection ongoing
ENGINEER WARD
NORTH KINANGOP WARD
| Githae Water Project- Supply of assorted pipes and fittings -North Kinangop Ward | North Kinangop | 1000000 | 0% | CGN | Site visit and data collection ongoing
| MURUNGARU WARD |  |  | 0% | CGN | Site visit and data collection ongoing
| Solarization of mutharaba borehole | Murungaru | 2000000 | 0% | CGN | Site visit and data collection ongoing
GETA WARD
| Kiambogo borehole- Erection of 50M3 steel water tank and related works | Geta | 3500000 | 0% | CGN | Site visit and data collection ongoing
| Supply of assorted pipes and accessories | Geta | 1500000 | 0% | CGN | Site visit and data collection ongoing
GITHIORO WARD
| Muhonia Turasha booster borehole- installation of submersible pump and solarization & construction of water tower and erection of 2No. 10M3 plastic tanks | Githioro | 6500000 | 0% | CGN | Site visit and data collection ongoing
| Aberdare WP- 100M3 Masonry tank at Migaa | Githioro | 2500000 | 0% | CGN | Site visit and data collection ongoing
| Supply of assorted pipes and accessories- Dry Area | Githioro | 500000 | 0% | CGN | Site visit and data collection ongoing
WANJOHI WARD
| Umoja borehole equipping- Submersible pump and solarization | Wanjohi | 4000000 | 0% | CGN | Site visit and data collection ongoing
| Umoja borehole -construction of water tower and erection of 50M3 steel water tank | Wanjohi | 3500000 | 0% | CGN | Site visit and data collection ongoing
| Umoja borehole assorted pipes | Wanjohi | 3000000 | 0% | CGN | Site visit and data collection ongoing
| Assorted pipes and fittings | Wanjohi | 4500000 | 0% | CGN | Site visit and data collection ongoing
KIPIPIRI WARD
| Kirima borehole steel tank | Kipipiri | 3500000 | 0% | CGN | Site visit and data collection ongoing
| Hawamwiko borehole- Equipping with submersible pump and solarization | Kipipiri | 4000000 | 0% | CGN | Site visit and data collection ongoing
| Suply and delivey of plastic water tanks | Kipipiri | 2000000 | 0% | CGN | Site visit and data collection ongoing
| Assorted pipes and accessories | Kipipiri | 2000000 | 0% | CGN | Site visit and data collection ongoing
KAIMBAGA WARD
| Supply of assorted water pipes | Kaimbaga | 3000000 | 0% | CGN | Site visit and data collection ongoing
KARAU WARD
| Gatarwa borehore -Supply and laying of pipes | Karau | 500000 | 0% | CGN | Site visit and data collection ongoing
| Mawingu borehole -supply and installation submersible pump and solarization system- Karau Ward | Karau | 5000000 | 0% | CGN | Site visit and data collection ongoing
| Muiri Borehole -Supply and laying of pipes | Karau | 500000 | 0% | CGN | Site visit and data collection ongoing
| Wilson borehole - Supply and laying of pipes | Karau | 500000 | 0% | CGN | Site visit and data collection ongoing
| Kagaa borehole -Supply and laying of pipes | Karau | 500000 | 0% | CGN | Site visit and data collection ongoing
| Githungo borehole - Supply and laying of pipes | Karau | 1000000 | 0% | CGN | Site visit and data collection ongoing
| Kirimaini borehole -supply and installation of solars and pumps | Karau | 4000000 | 0% | CGN | Site visit and data collection ongoing
RURII WARD
| Matura borehole -Supply and installation of submersible pump and solar panels and construction of powerhouse | Rurii | 4500000 | 0% | CGN | Site visit and data collection ongoing
| Huhoini Bosinia - Supply of pipes and accessories | Rurii | 1500000 | 0% | CGN | Site visit and data collection ongoing
KANJUIRI WARD
| Supply of Assorted Pipes to various Water Projects | Kanjuiri | 3000000 | 0% | CGN | Site visit and data collection ongoing
| Wiyumirie 100m3 masonry tank | Kanjuiri | 3000000 | 0% | CGN | Site visit and data collection ongoing
MIRANGINE WARD
| Matunda WP - Supply of pipes and accessories | Mirangine | 2500000 | 0% | CGN | Site visit and data collection ongoing
| Kurungu WP- Supply of pipes and accessories | Mirangine | 1500000 | 0% | CGN | Site visit and data collection ongoing
| Kihuho WP- Supply of pipes and accessories | Mirangine | 1500000 | 0% | CGN | Site visit and data collection ongoing
| Waichoho Village - Supply of pipes and accessories | Mirangine | 1000000 | 0% | CGN | Site visit and data collection ongoing
| Kahia BH WP- Supply and installation of booster pump | Mirangine | 1000000 | 0% | CGN | Site visit and data collection ongoing
| Assorted pipes and fittings | Mirangine | 2000000 | 0% | CGN | Site visit and data collection ongoing
CHARAGITA WARD
| Rehabilitation of Oraimutia water project |  | 0 | 0% | CGN | Site visit and data collection ongoing
WERU WARD
| Rehabilitation of Gathundia borehole | Weru | 2700000 | 0% | CGN | Site visit and data collection ongoing
| Supply of assorted pipes and fittings in Weru ward. | Weru | 3300000 | 0% | CGN | Site visit and data collection ongoing
| Drilling and Casing - Inooro Pry School Borehole | Weru | 3000000 | 0% | CGN | Site visit and data collection ongoing
| Inooro borehole wp- Supply and installation of submersible pump and solarization | Weru | 4000000 | 0% | CGN | Site visit and data collection ongoing
GATIMU WARD
| Supply and laying of assorted pipes and fittings in Gatimu. | Gatimu | 4000000 | 0% | CGN | Site visit and data collection ongoing
GATHANJI WARD
| Equipping Mwenja borehole | Gathanji | 1800000 | 0% | CGN | Site visit and data collection ongoing
| Construction of water tower and erection of 2-10M3 plastic tanks and water kiosk- Kabati/Mung'etho WP | Gathanji | 2500000 | 0% | CGN | Site visit and data collection ongoing
| Construction of water tower and erection of 2-10M3 plastic tanks - Gituamba WP | Gathanji | 1800000 | 0% | CGN | Site visit and data collection ongoing
| Rehabilitation of Boiman Borehole | Gathanji | 1500000 | 0% | CGN | Site visit and data collection ongoing
| KIRIITA |  |  | 0% | CGN | Site visit and data collection ongoing
| Construction of 100m3 steel tank - Leshau Karagoini | Kiriita | 5300000 | 0% | CGN | Site visit and data collection ongoing
SHAMATA
| Equipping Plot 17 Borehole with submersible pump and solars | Shamata | 5500000 | 0% | CGN | Site visit and data collection ongoing
| Installation of submersible pump- Shamata | Shamata | 1500000 | 0% | CGN | Site visit and data collection ongoing
| Shamata ward water works | Shamata | 3500000 | 0% | CGN | Site visit and data collection ongoing
| Hydrogeological survey, EIA, Drilling and casing Kihuko borehole & construction of a 100M3 Nazareth Masonry tank- Shamata ward | Shamata | 5498688 | 0% | CGN | Site visit and data collection ongoing
LESHAU PONDO
| Shauri Kianda Borehole- Flushing | Leshau Pondo | 250000 | 0% | CGN | Site visit and data collection ongoing
| Supply of assorted pipes and fittings -Leshau pondo | Leshau Pondo | 600000 | 0% | CGN | Site visit and data collection ongoing
Other ongoing works
| Rurii Plot 10 borehole WP-Infrastructure for dilution- 225M3 Masonry tank, Booster pump capable of delivering 20M3 at a head of 50M, solar panels 6KW, Control panel, solar structure, ultrasonic flow meters | Rurii | 5100000 | 0% | CGN | Site visit and data collection ongoing
| Rurii Plot 10 borehole WP- Water Reticulation | Rurii | 1600000 | 0% | CGN | Site visit and data collection ongoing
Pending Bills | Water infrastructural Development pending bills |  | 0 | 0% | CGN | Site visit and data collection ongoing
| Kagaa borehole drilling and casing - Karau ward- JOHNAPRIL LOGISTICS LIMITED FY 2023-24 | Karau | 2997280 | 0% | CGN | Site visit and data collection ongoing
| Drilling and casing of Kahiga Umoja B/h in Kipipiri ward JACKIEDANIEL ENTERPRISES | Kipipiri | 3083625 | 0% | CGN | Site visit and data collection ongoing
| Githima water project - supply and laying of pipes -Mirangine ward FADRAM ENTERPRISES | Mirangine | 2998300 | 0% | CGN | Site visit and data collection ongoing
| Nyandundo borehole drilling (Mirangine) and Weru-Kariko water project additional solar panels (Weru ward) - SHERLYN HOLDINGS LTD FY 2022-23 | Mirangine | 3999500 | 0% | CGN | Site visit and data collection ongoing
Water Sector Climate Change Resilience | OLWASCO - Assorted pipes and fittings |  | 2000000 | 0% | CGN | Site visit and data collection ongoing
| Nyandawas - Production and Consumer meters |  | 2000000 | 0% | CGN | Site visit and data collection ongoing
| Gatitu W/P 100M3 elavated steel tank - Weru ward | Weru | 5000000 | 0% | CGN | Site visit and data collection ongoing
Environment Management | Unclogging Storm Water Drainages- Ndaragwa Central | Ndaragwa Central | 1000000 | 0% | CGN | Site visit and data collection ongoing
| Tree planting in institutions- Ndaragwa Central | Ndaragwa Central | 1500000 | 0% | CGN | Site visit and data collection ongoing
Development Pending Bills
| Shamata -Supply of LPG gas cylinders 6Kg, Gas and burner-Simbara | Shamata | 1998731 | 0% | CGN | Site visit and data collection ongoing
| Supply of LPG cylinder to the Elderly- Olbolosat Shamata | Shamata | 2998380 | 0% | CGN | Site visit and data collection ongoing
Climate Change Resilience | World Bank- Financing Locally Led Climate Action Program (FLLOCA)- County Climate Resilience Investment Grant Bal b/f FY 2024-25 | Countywide | 136000000 | 60% | Donor | Ongoing
| World Bank- Financing Locally Led Climate Action Program (FLLOCA)- County Climate Resilience Investment Grant | Countywide | 104000000 | 0% | Donor | Community engagement ongoing
| County Contribution- Financing Locally Led Climate Action Program (FLLOCA)- County Climate Resilience Investment Grant-County Climate change fund | Countywide | 66000000 | 0% | CGN | Community engagement ongoing
| County Contribution - Financing Locally Led Climate Action Program (FLLOCA)- County Climate Resilience Investment Grant-County Climate change fund- County Contribution- Last mile reticulation - Rurii | Rurii | 4000000 | 0% | CGN | Community engagement ongoing
| County Contribution - Financing Locally Led Climate Action Program (FLLOCA)- County Climate Resilience Investment Grant-County Climate change fund- County Contribution- Last mile reticulation - Michore borehole | Michore | 4000000 | 0% | CGN | Community engagement ongoing
Natural Resources | Establishment of Model Subcounty (Kinangop, Ndaragwa) tree nurseries. | Kinangop, Ndaragwa | 700000 | 0% | CGN | Site visit and data collection ongoing
Tourism Development and Marketing | Tree planting in the Arboretum | Kaimbaga | 300000 | 0% | CGN | Site visit and data collection ongoing
| Establishing tourism enterprises | Countywide | 3000000 | 0% | CGN | Site visit and data collection ongoing
| Ol'Kalou arboretum- Developing Animal Sanctuary | Kaimbaga | 1500000 | 0% | CGN | Site visit and data collection ongoing
| Ol'Kalou arboretum- Developing VIP Parking lots | Kaimbaga | 1500000 | 0% | CGN | Site visit and data collection ongoing
| Ol'Kalou arboretum- Development of a biking and jogging trail in the Arboretum (Phase 2) | Kaimbaga | 3000000 | 0% | CGN | Site visit and data collection ongoing
AGRICULTURE, AGRIBUSINESS, LIVESTOCK AND FISHERIES
Livestock Production | Bee farming promotion - Supply and distribution of hives - Githioro Ward | Githioro Ward | 400000 | 0 | CGN | Procurement in process
| Githioro ward - Purchase and distribution of Incubators | Githioro Ward | 300000 | 0 | CGN | Procurement in process
| Charagita ward -Quality fodder promotion- Super Nappier | Charagita ward | 700000 | 0 | CGN | Procurement in process
| Shamata- Purchase and delivery of beehives | Shamata Ward | 100000 | 0 | CGN | Procurement in process
| Shamata ward -Quality fodder promotion | Shamata Ward | 300000 | 0 | CGN | Procurement in process
| Leshau Pondo ward - Purchase and distribution of poultry eggs and feeds | Leshau Pondo ward | 500000 | 0 | CGN | Procurement in process
| Poultry farming promotion - breeding stock and Inputs - Githioro Ward | Githioro Ward | 400000 | 0 | CGN | Specifications written to procurement section
| Wanjohi Ward- Support to sheep farmers group with parental stock | Wanjohi Ward | 800000 | 0 | CGN | Procurement in process
| Livestock farming promotion - breeding stock and Inputs - Ndaragwa Central Ward | Ndaragwa Central Ward | 1500000 | 0 | CGN | Procurement in process
| Charagita ward - sheep farming promotion- breeding stock | Charagita ward | 1500000 | 0 | CGN | Procurement in process
| Livestock farming promotion - breeding stock and Inputs - Rurii Ward | Rurii Ward | 900000 | 0 | CGN | Procurement in process
| Livestock farming promotion - breeding stock (heifers)- Leshau Pondo Ward | Leshau Pondo Ward | 720000 | 0 | CGN | Construction to kick start after contractor identification
| Mirangine ward - Livestock farming promotion- breeding stock | Mirangine ward | 1500000 | 0 | CGN | Market survey was done. Procurement process is ongoing
| Shamata Ward- Livestock promotion- Support to sheep farmers group with parental stock-Canary | Shamata Ward | 3000000 | 0 | CGN | Procurement in process
| Shamata Ward- Livestock promotion- Support to poultry farmers group with parental stock- Simbara | Shamata Ward | 3000000 | 0 | CGN | Procurement in process
| North Kinangop Ward- Livestock promotion- Support to sheep farmers group with parental stock | North Kinangop Ward | 2500000 | 0 | CGN | Market survey was done. Procurement process is ongoing
| National Government - Financial support to various livestock value chains | Selected Cooperatives across the County | 135210000 | 0 | Coolers to be procured by National Government | Not yet started
| Leshau Pondo ward - Ongoing construction of Livestock sale yard | Leshau Pondo Ward | 1000000 | 0 | CGN | Construction to kick start after contractor identification
| Development of feed centres - Kipipiri sub-county | Kipipiri sub-county | 1000000 | 0 | CGN | Site selection for feed center is ongoing
Veterinary Services | Vaccination equipment | Countywide | 1000000 | 0 | CGN | Not yet started
| Supplies for Production- Acaricides and drugs (East Coast Fever Control Program) | Countywide | 2400000 | 0 | CGN | Not yet started
| Purchase of vaccines & sera (vaccination program) | Countywide | 8639599 | 0 | CGN | Not yet started
| Repair of county slaughter houses | Countywide | 800000 | 0 | CGN | Not yet started
| Veterinary supplies and materials- liquid nitrogen | Countywide | 500000 | 0 | CGN | Not yet started
| Provision and administration of dairy semen (Inclusive of commission to AI Service providers) - Karau ward | Karau ward | 1000000 | 0 | CGN | Not yet started
| Establishment of an Artificial Insemination Management and Control Centre- (fabrication of container(s), supply of liquid nitrogen, sexed semen and related equipment, commission to providers etc) Eng. Ward | Engineer Ward | 3000000 | 0 | CGN | Not yet started
| Subsidized AI Programme - Inclusive of commission to AI Service providers (Kes. 1m/Ward) | Countywide | 25000000 | 0 | CGN | Not yet started
Fisheries Development | Stocking of dams and ponds with fingerlings | Countywide | 800000 | 0 | GoK | Process ongoing
| Supplies for Production-trout fish feeds and feed medicine | Countywide | 300000 | 0 | GoK | Process ongoing
| Refurbishment of fish trout farms | Ndaragwa and Geta trout farms | 700000 | 0 | GoK | Process ongoing
| Rehabilitation of hatchery units-Ndaragwa trout farm | Ndaragwa trout farm | 700000 | 0 | GoK | Process ongoing
Crop Development | Crop farming promotion (Farm inputs)- Kiriita | Kiriita | 3000000 | 0% | CGN
| Crop farming promotion - Supply of walk-behind tractor with potato harvesting equipment - Githabai Ward | Githabai | 500000 | 0% | CGN
| Market access support for agribusiness (Fuel to support maintenace/upgrade using County roadwork inhouse machinery)- Githabai Ward | Githabai | 3000000 | 0% | CGN
| Crop farming- Certified/Clean seeds - Nyakio Ward | nYakio | 1000000 | 0% | CGN
| Crop farming/ Horticultural promotion - North Kinangop Ward | North Kinangop Ward | 2000000 | 0% | CGN
| Crop farming promotion - Githioro Ward | Githioro ward | 300000 | 0% | CGN
| Crop farming promotion Certified seeds (Maize)- Kipipiri | Kipipiri | 1500000 | 0% | CGN
| Crop farming promotion - Karau | Karau ward | 0 | 0% | CGN
| Crop farming promotion - Certified seeds (Maize)- Karau ward | Karau ward | 1800000 | 0% | CGN
| Crop farming promotion - Certified seeds (Maize)- Rurii | Rurii Ward | 2000000 | 0% | CGN
| Crop farming promotion - Certified seeds (Maize)- Kaimbaga ward | Kaimbaga Ward | 2000000 | 0% | CGN
| Solar panel lithium battery for incubator- Kaimbaga ward | Kaimbaga Ward | 1000000 | 0% | CGN
| Support to Gatondo co-operatve society with potato seeds and herbicides - Wanjohi ward | Wanjohi | 800000 | 0% | CGN
| Crop farming promotion - Certified seeds (Maize)- Wanjohi ward | Wanjohi | 3000000 | 0% | CGN
| Crop farming promotion - Certified/Clean seeds (potato)- Wanjohi ward | Wanjohi | 1500000 | 0% | CGN
| Crop farming promotion - Mirangine | Mirangine | 1000000 | 0% | CGN
| Crop farming promotion - Gatimu | Gatimu | 0 | 0% | CGN
| Crop farming promotion (Certified maize seeds)- Leshau Pondo | Leshau Pondo Ward | 1250000 | 0% | CGN
| Crop farming promotion - Shamata | Shamata Ward | 3500000 | 0% | CGN
| Crop farming promotion (Certified maize seeds)- Ndaragwa Central | Ndaragwa Central Ward | 1000000 | 0% | CGN
| Crop farming promotion - Clean/certified seeds (Maize, peas etc)- Njabini | Njabini/Kiburu | 1000000 | 0% | CGN
| Propagation of potato seeds for Charagita at Ol'JoroOrok training centre - Charagita ward | Charagita | 3000000 | 0% | CGN
| IDA(World Bank) - National Agricultural Value Chain Development Project (NAVCDP) | Countywide | 151520000 | 8% | WORLD BANK
| National Agricultural Value Chain Development Project (NAVCDP) - County contribution FY 2024/2025/ 2025/2026 | Countywide | 10000000 | 1% | CGN
| Kenya Agricultural Business Development Project (KABDP) | Countywide | 10920000 | 0% | IFAD
| Kenya Agricultural Business Development Project (KABDP) county contribution | Countywide | 3000000 | 0% | CGN
| Input subsidy - Procurement and distribution of subsidized fertilizer | Countywide | 123620000 | 58% | CGN | Part of the fertilizer was previous years balance
| Distribution of subsidized fertilizer | Countywide | 2000000 | 58% | CGN
Agricultural Insitutions' Suppport | Agriculture Institutions' Revolving Fund- Ol'Joro'Orok ATC, Njabini ATC, Nyahururu & Kinangop Agricultural Mechanization Services (AMS) and Seed Production Unit | County Agricultural Institutions - Countywide | 5000000 | 72% | CGN | Some payments for last financial year were cleared this financial year. The account had previous years balance
LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT
Land Management | Acquired specialized equipment (mapping drone) | HQ | 10000000 | 0% | CGN | Not started
| Acquisition of land for Kiambogo cooperative | Geta ward | 2000000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- Magumu | Magumu ward | 1800000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- Nyakio | Nyakio ward | 2000000 | 0% | CGN | Not started
| Acquisition of land for Nyakio cemetery | Nyakio ward | 6000000 | 0% | CGN | Not started
| Acquisition of land for Miti-iri borehole- | Githabai ward | 1000000 | 0% | CGN | Not started
| Acquisition of land for public amenities/ Chuma ECDE Land - Gathaara | Gathaara ward | 600000 | 0% | CGN | Not started
| Acquisition of land for Maina-Munoru- Mutamaiyu access road - Gathaara | Gathaara ward | 1000000 | 0% | CGN | Not started
| Acquisition of land for Norfolk-Kariahu access road- | Gathaara ward | 1000000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- | North Kinangop ward | 1500000 | 0% | CGN | Not started
| Acquisition of land for Maningi ECDE- Githioro | Githioro ward | 500000 | 0% | CGN | Not started
| Acquisition of land for Ithagu access road Turasha- Githioro | Githioro ward | 1000000 | 0% | CGN | Not started
| Acquisition of land for Kibonde Access Road | Githioro ward | 250000 | 0% | CGN | Not started
| Acquisition of land for Kieni access road- | Kaimbaga ward | 800000 | 0% | CGN | Not started
| Acquisition of land for access road to dam and other public amenities- Silanga- | Rurii ward | 1000000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities-- | Rurii ward | 1500000 | 0% | CGN | Not started
| Acquisition of land for public amenities- Kiambururu Borehole- | Kanjuiri ward | 800000 | 0% | CGN | Not started
| Acquisition of land for public amenities- Charagita public toilet | Charagita ward | 3000000 | 0% | CGN | Not started
| Acquisition of land for access roads Mikeu- | Gathanji Ward | 200000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- | Gatimu ward | 2000000 | 0% | CGN | Not started
| Acquisition of land for Thaba ECDE (Leah Wanjiku Kung'u) - | Karau Ward | 800000 | 0% | CGN | Not started
| Acquisition of land for Ndeiya ECDE - | Wanjohi ward | 1200000 | 0% | CGN | Not started
| Acquisition of land for access road | Wanjohi ward | 1200000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- Mbuyu Kahuho Community social hall- | Leshau Pondo ward | 600000 | 0% | CGN | Not started
| Acquisition of land for Kandeto - Chege Access Road - | Karau Ward | 2000000 | 0% | CGN | Not started
| Acquisition of Gituamba Road access road- Mirangine | Mirangine ward | 2000000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- Nyakiambi- Gichia Access Road- Mirangine | Mirangine ward | 1100000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- Kibendera Pry Sch Access Road- | Mirangine ward | 800000 | 0% | CGN | Not started
| Acquisition of land for access roads and other public amenities- | Shamata ward | 1500000 | 0% | CGN | Not started
| Acquisition of land for Mirangine Stadium | Mirangine ward | 7000000 | 0% | CGN | Not started
| Acquisition of land for Engineer Stadium | Engineer ward | 6000000 | 0% | CGN | Not started
| Acquisition of land for access road to the Engineer market | Engineer ward | 1800000 | 0% | CGN | Not started
| Acquisition of Land for Engineer municipality dumpsite | Engineer ward | 10000000 | 0% | CGN | Not started
| Acquisition of Land for Mairo-Inya municipality dumpsite | Kiriita ward | 10000000 | 0% | CGN | Not started
PHYSICAL PLANNING | Completion of physical and development land use plans for Leshau, Igwamiti, Kiriogo, Michore and Njabini |  | 2100000 | 0% | CGN | Not started
Urban Development | Construction of concrete water point in Miharati market- | Kipipiri Ward | 500000 | 0% | CGN | Not started
| Oljororok Town drainage works | Weru ward | 2000000 | 0% | CGN | Not started
| Public toilet- Mawingu in Githioro Ward | Githioro Ward | 2000000 | 0% | CGN | Not started
| Upgrade of towns- Nyakio | Nyakio ward | 2000000 | 0% | CGN | Not started
| Njabini Drainage works- Njabini Ward | Njabini Ward | 2000000 | 0% | CGN | Not started
HOUSING | County houses rehabilitation (Huruma and Bahati Estates) and Nyandarua County Houses -Nyahururu | Kaimbaga ward | 4000000 | 0% | CGN | Not started
OL KALOU Municipality | Procurement of skip bins | Ol Kalou Municipality | 2000000 | 0% | CGN | Not started
| Procurement of furniture for the social hall and paving block plant | Ol Kalou Municipality | 1000000 | 0% | CGN | Not started
| Leveling and beautification of social hall compound | Ol Kalou Municipality | 700000 | 0% | CGN | Not started
| Procurement of a garbage truck | Ol Kalou Municipality | 13500000 | 0% | CGN | Not started
ENGINEER Municipality | Procurement of skip bins | ENGINEER Municipality | 3000000 | 0% | CGN | Not started
| Procurement of litter bins | ENGINEER Municipality | 500000 | 0% | CGN | Not started
| Procurement of office furniture | ENGINEER Municipality | 1400000 | 0% | CGN | Not started
| Procurement of garbage truck | ENGINEER Municipality | 13500000 | 0% | CGN | Not started
| Renovation of offices | ENGINEER Municipality | 1000000 | 0% | CGN | Not started
MAIRO-INYA Municipality | Procurement and distribution of of skip bins in Kiriita, Leshau pondo, Ndaragwa Central, Gatimu wards | MAIRO-INYA Municipality | 4800000 | 0% | CGN | Not started
| Procurement of a garbage truck | MAIRO-INYA Municipality | 13500000 | 0% | CGN | Not started
ROADS, TRANSPORT, ENERGY & PUBLIC WORKS
Roads development
| Road improvement and maintenance using county in-house roadwork machinery | magumu | 9500000 | 0% | CGN | Data collection and BQ preparation
| Wa Monicah Road | magumu | 3500000 | 0% | CGN | Data collection and BQ preparation
| Wa Nyambura Road | magumu | 3000000 | 0% | CGN | Data collection and BQ preparation
| Jeremiah Road | magumu | 2500000 | 0% | CGN | Data collection and BQ preparation
| Wamuthoni Road | magumu | 2500000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | magumu | 2200000 | 0% | CGN | Data collection and BQ preparation
| Assorted roadworks | magumu | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | nyakio | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | nyakio | 6000000 | 0% | CGN | Data collection and BQ preparation
| Assorted Roadworks- Nyakio | nyakio | 3000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts- Nyakio | nyakio | 2000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | nyakio | 2000000 | 0% | CGN | Data collection and BQ preparation
| Rebecca Road Nyakio | nyakio | 2000000 | 0% | CGN | Data collection and BQ preparation
| Mukiri Roads- Nyakio | nyakio | 5000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | githabai | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | githabai | 15000000 | 0% | CGN | Data collection and BQ preparation
| Kiarie Road | githabai | 3000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | githabai | 3000000 | 0% | CGN | Data collection and BQ preparation
| Assorted Culverts- Githabai Ward | githabai | 3000000 | 0% | CGN | Data collection and BQ preparation
| Drainage works - Labour based contracting | githabai | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Njabini | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance hired machinery (Framework) | Njabini | 3500000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Njabini | 3000000 | 0% | CGN | Data collection and BQ preparation
| Coloboise Roads | Njabini | 5000000 | 0% | CGN | Data collection and BQ preparation
| Ngero- Gikuyu Road | Njabini | 2000000 | 0% | CGN | Data collection and BQ preparation
| Assorted roadworks-Njabini | Njabini | 2500000 | 0% | CGN | Data collection and BQ preparation
| Assorted culvert installation and drainage works- Njabini Ward | Njabini | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Gathaara | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Gathaara | 6000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Gathaara | 3000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | Gathaara | 2000000 | 0% | CGN | Data collection and BQ preparation
| Kihara Road | Gathaara | 2000000 | 0% | CGN | Data collection and BQ preparation
| Assorted contractual roadworks | Gathaara | 4000000 | 0% | CGN | Data collection and BQ preparation
| Drainage works - Labour based contracting | Gathaara | 1000000 | 0% | CGN | Data collection and BQ preparation
| Fuel for county in-house machinery - Gathaara ward | Gathaara | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Engineer | 2000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Engineer | 9800000 | 0% | CGN | Data collection and BQ preparation
| Hire of Machinery | Engineer | 7260000 | 0% | CGN | Data collection and BQ preparation
| Mwenja Road | Engineer | 2372917 | 0% | CGN | Data collection and BQ preparation
| Good Samaritan- Kibabui Road | Engineer | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | North kinangop | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | North kinangop | 5500000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | North kinangop | 1500000 | 0% | CGN | Data collection and BQ preparation
| Bypass Road | North kinangop | 2500000 | 0% | CGN | Data collection and BQ preparation
| Karemeri Road | North kinangop | 2000000 | 0% | CGN | Data collection and BQ preparation
| Nandarasi Road | North kinangop | 2000000 | 0% | CGN | Data collection and BQ preparation
| Ezekiel road completion | North kinangop | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Murungaru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Murungaru | 3000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Murungaru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Kabata road | Murungaru | 1000000 | 0% | CGN | Data collection and BQ preparation
| Kamirangi concrete (Phase 2) | Murungaru | 1000000 | 0% | CGN | Data collection and BQ preparation
| Shamata Mikaro concrete (Phase 2) | Murungaru | 1000000 | 0% | CGN | Data collection and BQ preparation
| Kamau Kang'ethe road | Murungaru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Pastor Wakavii Mkungi road | Murungaru | 1500000 | 0% | CGN | Data collection and BQ preparation
| Gaturi Wathiong'o Saba road | Murungaru | 2500000 | 0% | CGN | Data collection and BQ preparation
| Ndemu (Hianyu) road | Murungaru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | Murungaru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Wangunini- Boro Road | Murungaru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Geta | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Geta | 8000000 | 0% | CGN | Data collection and BQ preparation
| Gakorofa Road | Geta | 2000000 | 0% | CGN | Data collection and BQ preparation
| No. 40 - Gichigi - Gaichukuru Road | Geta | 3000000 | 0% | CGN | Data collection and BQ preparation
| No. 22 Kianjogu Road | Geta | 4500000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel for Road improvement and maintenance using county inhouse machinery and hired machinery (Framework) | Geta | 3000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts- Geta Ward | Geta | 1545400 | 0% | CGN | Data collection and BQ preparation
| Kagimbi- Rutuba- Marimbi Road | Geta | 3000000 | 0% | CGN | Data collection and BQ preparation
| Kwa Matu - Matangi Road | Geta | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Githioro | 3000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel and road improvement and maintenance using hired machinery (Framework) | Githioro | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery- Gathiriga Roads | Githioro | 2000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Githioro | 800000 | 0% | CGN | Data collection and BQ preparation
| Grading and spot patching of Konoike road & grading and graveling of Waititu and Njara Roads | Githioro | 4500000 | 0% | CGN | Data collection and BQ preparation
| Sobos - Karungo road, Maingi Road & Cucu Mother Road | Githioro | 5000000 | 0% | CGN | Data collection and BQ preparation
| Grading and graveling of Wangui Road & Grading and spot patching of Kibuya Road | Githioro | 3000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts- Turasha Area- Githioro Ward | Githioro | 600000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts- Githioro Ward | Githioro | 1200000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Kipipiri | 4000000 | 0% | CGN | Data collection and BQ preparation
| Foothill - Karandi Road | Kipipiri | 2600000 | 0% | CGN | Data collection and BQ preparation
| Wa Kimotho Road | Kipipiri | 2000000 | 0% | CGN | Data collection and BQ preparation
| Martin Road | Kipipiri | 3000000 | 0% | CGN | Data collection and BQ preparation
| Wa Maina Road | Kipipiri | 1000000 | 0% | CGN | Data collection and BQ preparation
| Kangomongo | Kipipiri | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Wanjohi | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Wanjohi | 9000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Wanjohi | 4000000 | 0% | CGN | Data collection and BQ preparation
| Ndeiya - Small Aden road | Wanjohi | 3000000 | 0% | CGN | Data collection and BQ preparation
| Magomano ECDE - Thing'oru dam road | Wanjohi | 2500000 | 0% | CGN | Data collection and BQ preparation
| Kihonge -Mubau road | Wanjohi | 2000000 | 0% | CGN | Data collection and BQ preparation
| Rayetta Road- Spot patching and drainage works | Wanjohi | 5000000 | 0% | CGN | Data collection and BQ preparation
| Mutongoria - Mubau road | Wanjohi | 5000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Kaimbaga | 5000000 | 0% | CGN | Data collection and BQ preparation
| JM primary - Mahee road | Kaimbaga | 4500000 | 0% | CGN | Data collection and BQ preparation
| Gitau - Rumathi road | Kaimbaga | 2000000 | 0% | CGN | Data collection and BQ preparation
| Gichungo road | Kaimbaga | 4500000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | Kaimbaga | 1000000 | 0% | CGN | Data collection and BQ preparation
| Karima Road - Kaimbaga | Kaimbaga | 5000000 | 0% | CGN | Data collection and BQ preparation
| Sewage Road - Kaimbaga | Kaimbaga | 5000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Karau | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Karau | 4500000 | 0% | CGN | Data collection and BQ preparation
| Thaba road | Karau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Muiri road | Karau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Mawingu road | Karau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Kirimaini road | Karau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Mariba road | Karau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Rurii | 4000000 | 0% | CGN | Data collection and BQ preparation
| Njuru Githunguri Road | Rurii | 3000000 | 0% | CGN | Data collection and BQ preparation
| Mbichu Kauru Road (Mchope) | Rurii | 1500000 | 0% | CGN | Data collection and BQ preparation
| Silanga Wanyoike Road | Rurii | 1500000 | 0% | CGN | Data collection and BQ preparation
| Wahinya - Gichungo Road (Mugathika) | Rurii | 1500000 | 0% | CGN | Data collection and BQ preparation
| Mugathika- Petrol Road | Rurii | 4000000 | 0% | CGN | Data collection and BQ preparation
| Kiyuu- Wa Marigo Road | Rurii | 2000000 | 0% | CGN | Data collection and BQ preparation
| Mathenge Kiboi Road- Bush clearing and drainage works- Labour contracting | Rurii | 1000000 | 0% | CGN | Data collection and BQ preparation
| Kibaki-Wangai- Henry Road | Rurii | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Kanjuiri | 2000000 | 0% | CGN | Data collection and BQ preparation
| Mbata- Kanjuiri Junction Road | Kanjuiri | 2500000 | 0% | CGN | Data collection and BQ preparation
| Mbata - Kang'athia Junction | Kanjuiri | 2500000 | 0% | CGN | Data collection and BQ preparation
| Rutara - Githioro Road | Kanjuiri | 2000000 | 0% | CGN | Data collection and BQ preparation
| Tumani- Gishagi Road | Kanjuiri | 2200000 | 0% | CGN | Data collection and BQ preparation
| Mbata-Kirathimo Road | Kanjuiri | 5000000 | 0% | CGN | Data collection and BQ preparation
| Murindati Pry Junction- Kiambururu Junction | Kanjuiri | 2500000 | 0% | CGN | Data collection and BQ preparation
| Chamuka Road | Kanjuiri | 1500000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Mirangine | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Mirangine | 6000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Mirangine | 2800000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery- MOA Village Roads | Mirangine | 3000000 | 0% | CGN | Data collection and BQ preparation
| Kihuho Nursery- Timothy Road | Mirangine | 4000000 | 0% | CGN | Data collection and BQ preparation
| Nene Road | Mirangine | 1000000 | 0% | CGN | Data collection and BQ preparation
| Douglas Road | Mirangine | 1500000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | Mirangine | 2100000 | 0% | CGN | Data collection and BQ preparation
| Kurungu- Headqurter Road | Mirangine | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | weru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | weru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | weru | 2000000 | 0% | CGN | Data collection and BQ preparation
| SK- Memia Road | weru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Gikurumi - Iria-ini | weru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Concrete work- Kwa Moshu & Chief Kihuru sections | weru | 3900000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Charagita | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery (Framework) | Charagita | 8000000 | 0% | CGN | Data collection and BQ preparation
| Gitangi road | Charagita | 2000000 | 0% | CGN | Data collection and BQ preparation
| Dam road | Charagita | 1600000 | 0% | CGN | Data collection and BQ preparation
| Thayu road | Charagita | 2000000 | 0% | CGN | Data collection and BQ preparation
| Ngano township road | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| PBK road | Charagita | 2000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts | Charagita | 1500000 | 0% | CGN | Data collection and BQ preparation
| Gachuiro and Kamuyu concrete on a hill | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| Ngorongo David road | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| Kabucho Road | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| Gichaka road - Charagita ward | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| Gacheru road - Charagita ward | Charagita | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Gathanji | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Gathanji | 4000000 | 0% | CGN | Data collection and BQ preparation
| Dedan -Gachomo Road | Gathanji | 1500000 | 0% | CGN | Data collection and BQ preparation
| Sila Road | Gathanji | 1700000 | 0% | CGN | Data collection and BQ preparation
| Gwa Chui Road | Gathanji | 1800000 | 0% | CGN | Data collection and BQ preparation
| Concrete works on a section of Chania Road | Gathanji | 1500000 | 0% | CGN | Data collection and BQ preparation
| Kinyanjui Road | Gathanji | 3000000 | 0% | CGN | Data collection and BQ preparation
| Kambaa Road | Gathanji | 3000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Gatimu | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Gatimu | 6500000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Gatimu | 2500000 | 0% | CGN | Data collection and BQ preparation
| Assorted cuverts- Gatimu | Gatimu | 2000000 | 0% | CGN | Data collection and BQ preparation
| Pace- Wachira Road | Gatimu | 4000000 | 0% | CGN | Data collection and BQ preparation
| Kanguo Road | Gatimu | 2000000 | 0% | CGN | Data collection and BQ preparation
| Runda B Road | Gatimu | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Kiriita | 4000000 | 0% | CGN | Data collection and BQ preparation
| Cabro Works- Kiriita Ward | Kiriita | 4000000 | 0% | CGN | Data collection and BQ preparation
| Ralph Mwaniki Road | Kiriita | 4000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Kiriita | 5500000 | 0% | CGN | Data collection and BQ preparation
| Ziwaka Roads | Kiriita | 5000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Kiriita | 1500000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using county in-house roadwork machinery | Leshau | 2000000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Leshau | 3000000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Leshau | 1000000 | 0% | CGN | Data collection and BQ preparation
| Shauri- Kianda Road | Leshau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Maina- Gachuhi Road | Leshau | 2000000 | 0% | CGN | Data collection and BQ preparation
| Raicheri Road | Leshau | 2000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts- Leshau pondo | Leshau | 1000000 | 0% | CGN | Data collection and BQ preparation
| Jerusha- Shauri 2 | Leshau | 1500000 | 0% | CGN | Data collection and BQ preparation
| Ndaragwa TVET Road- Grading and culvert installation | Leshau | 700000 | 0% | CGN | Data collection and BQ preparation
| Simba- Kararau Road- Grading and gravelling and culvert installation | Leshau | 3000000 | 0% | CGN | Data collection and BQ preparation
| Muruai road | Ndaragwa | 2000000 | 0% | CGN | Data collection and BQ preparation
| Wangui Bridge road | Ndaragwa | 1000000 | 0% | CGN | Data collection and BQ preparation
| New Kahuthu road | Ndaragwa | 1000000 | 0% | CGN | Data collection and BQ preparation
| Thuita road | Ndaragwa | 1500000 | 0% | CGN | Data collection and BQ preparation
| Subuku road | Ndaragwa | 1500000 | 0% | CGN | Data collection and BQ preparation
| Zaire road | Ndaragwa | 1500000 | 0% | CGN | Data collection and BQ preparation
| Muricho road | Ndaragwa | 2000000 | 0% | CGN | Data collection and BQ preparation
| Kiharo road | Ndaragwa | 1500000 | 0% | CGN | Data collection and BQ preparation
| Muti Umwe road | Ndaragwa | 1000000 | 0% | CGN | Data collection and BQ preparation
| Tafaria dam road | Ndaragwa | 1500000 | 0% | CGN | Data collection and BQ preparation
| Road improvement and maintenance using hired machinery | Shamata | 6200000 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | Shamata | 1800000 | 0% | CGN | Data collection and BQ preparation
| Ex-Daya Road | Shamata | 5000000 | 0% | CGN | Data collection and BQ preparation
| Kihuko Road | Shamata | 5200000 | 0% | CGN | Data collection and BQ preparation
| Gitobu Road | Shamata | 5000000 | 0% | CGN | Data collection and BQ preparation
| Muhakaini Road | Shamata | 5100000 | 0% | CGN | Data collection and BQ preparation
| Gakoe - Kianda Road | Shamata | 5000000 | 0% | CGN | Data collection and BQ preparation
| Badilisha Road | Shamata | 5000000 | 0% | CGN | Data collection and BQ preparation
| Kamaina Pry- Iria-ini Road Weru | Weru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Assorted culverts -Weru | Weru | 2000000 | 0% | CGN | Data collection and BQ preparation
| Colonial village Roads - Nyakio | nyakio | 4000000 | 0% | CGN | Data collection and BQ preparation
| Bara-Inya Road- Nyakio | nyakio | 4000000 | 0% | CGN | Data collection and BQ preparation
| Wandirangu- Wamugi Road - Weru Ward | Weru | 4000000 | 0% | CGN | Data collection and BQ preparation
| Nguirubi road- Wanjohi Ward | wanjohi ward | 4000000 | 0% | CGN | Data collection and BQ preparation
| Chief King'ori Road - Kaimbaga | kaimbaga | 4000000 | 0% | CGN | Data collection and BQ preparation
| Kibuki-Kamathi Road-Engineer | Eeeu | 4000000 | 0% | CGN | Data collection and BQ preparation
| Thiong'o Road- Githioro Ward | githioro ward | 4000000 | 0% | CGN | Data collection and BQ preparation
| 410 Bridge - Dispensary Road - North Kinangop | north kinangop | 4000000 | 0% | CGN | Data collection and BQ preparation
| Matini Road- Kipipiri Ward | kipipiri ward | 4000000 | 0% | CGN | Data collection and BQ preparation
| Wa Kamau Road - Gatimu Ward | gatimu | 4000000 | 0% | CGN | Data collection and BQ preparation
| Gathanji Ward- Kwa Mambo - Kiratu Road | gathanji | 4000000 | 0% | CGN | Data collection and BQ preparation
| Sheria Road- Githabai | githabai | 4000000 | 0% | CGN | Data collection and BQ preparation
| Njabini Ward- Churiri Road | njabini | 4000000 | 0% | CGN | Data collection and BQ preparation
| Charagita Ward- Oraimutia Road | charagita | 4000000 | 0% | CGN | Data collection and BQ preparation
| Kiriita Ward- 3 ways Road | kiriita | 4000000 | 0% | CGN | Data collection and BQ preparation
| Kanjuiri Ward- Wiyumiririe - Gathima Road | kanjuiri | 4000000 | 0% | CGN | Data collection and BQ preparation
| Shamata Ward - Njamba road | shamata | 4000000 | 0% | CGN | Data collection and BQ preparation
| Karau Ward- Gatarwa-Kamaru Road | karau | 4000000 | 0% | CGN | Data collection and BQ preparation
| General road maintenance | various | 15000000 | 0% | CGN | Data collection and BQ preparation
| Road Maintenance Levy Fund FY 2024-25 Unspent balance | various | 222822888 |  | CGN | Amount transferred to SPA ready for implementation
| Road Maintenance Levy Fund FY 2025-26 | various | 222822888 | 0% | CGN | Data collection and BQ preparation
Ongoing works/ Development Pending bills | Moses Bridge- Engineer | engineer | 1827083 | 0% | CGN | Data collection and BQ preparation
| Assorted grading works and road improvement works for Kiruthu road - Ndaragwa Central- M/S BERTRICON INVESTMENT LIMITED FY 2020/21 | ndaragwa | 3998600 | 0% | CGN | Data collection and BQ preparation
| Supply of gravel | various | 15000000 | 0% | CGN | Data collection and BQ preparation
Energy Section | Installation of lightening arresters across Yaang'a, Bongo and Kageraini among other sections- Nyakio | nyakio | 1500000 | 0% | CGN | Data collection and BQ preparation
| Installation of 20 Metre heigh Floodlight Ha Ikafu- Magumu | magumu | 1400000 | 0% | CGN | Data collection and BQ preparation
| Installation of 20 Metre heigh Floodlight (Kirima Borehole)- Kipipiri ward | kipipiri ward | 2800000 | 0% | CGN | Data collection and BQ preparation
| Installation of 2No. 13M floodlight- Kanyenyaini Junction & Polytechnic - Njabini | njabini | 800000 | 0% | CGN | Data collection and BQ preparation
| Relocation (and equipping) floodlight from Geta Market to Mibiriti Centre- Geta | geta | 700000 | 0% | CGN | Data collection and BQ preparation
| Installation of 3No. 13 Metre height Floodlight-Kaimbaga ward | kaimbaga | 1200000 | 0% | CGN | Data collection and BQ preparation
| Installation of 2No. 13 Metre height Floodlights (kwa Muchemi and Charagita) - Charagita ward ward | charagita | 800000 | 0% | CGN | Data collection and BQ preparation
| Installation of 5No. 13M Metre height Floodlights -Mirangine | mirangine | 2000000 | 0% | CGN | Data collection and BQ preparation
| Installation of 2No. 13 Metre height Floodlights-Gatimu | gatimu | 800000 | 0% | CGN | Data collection and BQ preparation
| Githunguri Ha Muchai Transformer- Rurii Ward | rurii | 1500000 | 0% | CGN | Data collection and BQ preparation
| Kiganjo B transformer maximization (Ha Mugi) - Kaimbaga | kaimbaga | 2000000 | 0% | CGN | Data collection and BQ preparation
| Power connection (KPLC)- Gathiriga Dispensary - Githioro | githioro ward | 50000 | 0% | CGN | Data collection and BQ preparation
| Installation of transformer- Njikimuka farm in Kimuri Sec Area- Murungaru Ward | murungaru | 1500000 | 0% | CGN | Data collection and BQ preparation
| Installation of 20M Floodlight- Rutara Maximum Centre, Kirathimo Cente and Kihoto Centre- Kanjuiri Ward | kanjuiri | 4500000 | 0% | CGN | Data collection and BQ preparation
Public works section | Bodaboda sheds (Gordan)- Leshau Pondo Ward | leshau pondo | 400000 | 0% | CGN | Data collection and BQ preparation
| Waiting Bay shed- Gitawa- Gathaara Ward | gathaara | 250000 | 0% | CGN | Data collection and BQ preparation
| Fencing Wanjohi VTC- Wanjohi Ward | wanjohi ward | 2000000 | 0% | CGN | Data collection and BQ preparation
| Fencing Mukeu ECDE - Nyakio Ward | nyakio | 1000000 | 0% | CGN | Data collection and BQ preparation
| Operationalization of paving block plant(purchase of moulds) | headquarters | 5000000 | 0% | CGN | Data collection and BQ preparation
| Branding of bodaboda sheds- Leshau Pondo Ward | leshau pondo | 400000 | 0% | CGN | Data collection and BQ preparation
| Construction of a Bodaboda shed- Kaimbaga | kaimbaga | 400000 | 0% | CGN | Data collection and BQ preparation
| Construction of a Bodaboda shed- Magumu | magumu | 400000 | 0% | CGN | Data collection and BQ preparation
| Construction of a Bodaboda shed- Ha Ikafu- Magumu | magumu | 400000 | 0% | CGN | Data collection and BQ preparation
| 2No. Bodaboda sheds (Rutara Maximum and Murindati Base)- Kanjuiri Ward | kanjuiri | 800000 | 0% | CGN | Data collection and BQ preparation
| 2No. Bodaboda sheds (Muteng'uri and DN)- Wanjohi Ward | wanjohi ward | 800000 | 0% | CGN | Data collection and BQ preparation
| 1No. Bodaboda shed (Muchemi trading centre)- Charagita Ward | charagita | 400000 | 0% | CGN | Data collection and BQ preparation
| 4No. Bodaboda sheds (Silanga, Jericho, Mukindu, Mairo)- Rurii Ward | rurii | 1600000 | 0% | CGN | Data collection and BQ preparation
| Box culverts- Wanjihia - Marimu B Road - Geta Ward | geta | 1700000 | 0% | CGN | Data collection and BQ preparation
Flagship Projects | Governor's residence | headquarters | 10000000 | 62% | CGN | Data collection and BQ preparation
| Cabro Works - Kasuku Centre - Weru Ward | Weru | 6000000 | 0% | CGN | Data collection and BQ preparation
| Renovation of buildings (Ol'Kalou subcounty and Enforcement)gutted down by fire | headquarters | 10000000 | 0% | CGN | Data collection and BQ preparation
| Construction of Gachuha Bridge - Githioro | githioro ward | 15000000 | 10% | CGN | second phase ongoing
| Construction of Kirika -Wanjohi River Bridge | wanjohi ward | 4000000 | 0% | CGN | Data collection and BQ preparation
| Gwa-Kiongo- Town Drainage and cabro works- Mirangine | mirangine | 5000000 | 0% | CGN | Data collection and BQ preparation
| Construction of Box culvert bridge- Shamata | shamata | 3000000 | 0% | CGN | Data collection and BQ preparation
| County headquarters (County contribution) | headquarters | 30000000 | 60% | CGN | ongoing
| County headquarters (National contribution) | headquarters | 121000000 | 60% | National gvt. | ongoing
Trade, Industrialization, Cooperative Development and Partnership
| Equipment support to Cottage industries (Captain and Geta) | Kaimbaga, Geta | 2400000 | 0 | CGN | Not yet implemented
| Fencing of CIDCs (Ndunyu Njeru, Geta and Ol-joro-orok Juakali centres) | North Kinangop, Geta, Weru | 2000000 | 0 | CGN | Not yet implemented
| Equipping of MSEs in the cottage industry (Gathanji) | Gathanji | 1500000 | 0 | CGN | Not yet implemented
| Electricity Connection in CIDCs Countywide | Countywide | 1000000 | 0 | CGN | Not yet implemented
| Leveling and compaction of Geta Juakali centre | Geta | 1000000 | 0 | CGN | Not yet implemented
| Supply and deliver Energy Saving Jikos - Ndaragwa Central | Ndaragwa Central | 2000000 | 0 | CGN | Not yet implemented
| Support to bodaboda groups - Gathanji Ward | Gathanji | 1000000 | 0 | CGN | Not yet implemented
| Supply and deliver Tents to social welfare groups - Gathanji Ward | Gathanji | 1000000 | 0 | CGN | Not yet implemented
| Upgrading of markets- Ol-joro-orok - Weru Ward | Weru | 1000000 | 0 | CGN | Not yet implemented
| Upgrade of Packhouse ground to ASK Show ground | Kaimbaga | 10000000 | 0 | CGN | Not yet implemented
| Karangatha Market Rehabilitation - Nyakio ward | Nyakio | 1000000 | 0 | CGN | Not yet implemented
| Maintenance of markets | Countywide | 2000000 | 0 | CGN | Not yet implemented
| Rehabilitation and Maintenace of Njabini Market | Njabini | 1000000 | 0 | CGN | Not yet implemented
| Upgrade of Githabai Market | Githabai | 1000000 | 0 | CGN | Not yet implemented
| Rehabilitation and maintenance (Boiman) - Gathanji | Gathanji | 1000000 | 0 | CGN | Not yet implemented
| Construction of a Public toilet -Muthiga Trading Centre - Leshau Pondo | Leshau pondo | 800000 | 0 | CGN | Not yet implemented
| Meter separation for Geta Market stalls | Geta | 1500000 | 0 | CGN | Not yet implemented
| Feasibility study Soko Mpya - URBAN EDGE MAZINGIRA | Magumu | 1485960 | 0 | CGN | Not yet implemented
| Support to farmers cooperatives (seeds/seedlings, milk cans etc) | Countywide | 2000000 | 0 | CGN | Not yet implemented
| Support Mikeu Cooperative Society with a motor cycle | Geta | 300000 | 0 | CGN | Not yet implemented
| Support to Gwami United Sacco - Installation of Internet and Softwares- Mirangine ward | Mirangine | 1000000 | 0 | CGN | Not yet implemented
| Support to Kinangop boost Sacco - Installation of software - Njabini ward | Njabini | 2500000 | 0 | CGN | Not yet implemented
| Support to Aberdare Sacco installation of software - Gathaara ward | Gathaara | 2500000 | 0 | CGN | Not yet implemented
| Support to Olkalou Dairy Co-operative Society - Purchase of desktops and installation of internet - Kaimbaga ward | Kaimbaga | 1000000 | 0 | CGN | Not yet implemented
| Support to Nyamarura sacco - purchase of desktops and installation of internet - Charagita | Charagita | 1000000 | 0 | CGN | Not yet implemented
| Support to Nyanda Sacco -Training materials and stationery support- Kiriita Ward | Kiriita | 2500000 | 0 | CGN | Not yet implemented
| Support to Ranyana Co-operative society - Ndaragwa Central | Ndaragwa Central | 1000000 | 0 | CGN | Not yet implemented
| Support to co-operatives with 50 litres capacity milk cans - Ndaragwa Central | Ndaragwa Central | 1000000 | 0 | CGN | Not yet implemented
| Renovation of Malewa Co-operative Society offices - Kipipiri ward | Kipipiri | 1500000 | 0 | CGN | Not yet implemented
| Inaugural Nyandarua County Investors Conference | Olkalou | 10000000 | 0 | CGN | Not yet implemented
| Prepared by: |  |  |  |  | Signed:
Designation
Date:
| Approved by Accounting Officer: |  |  |  |  | Signed:
Designation
Date: